## Data
Project Name | Task | Parent | Project | Assigned To | PM Progress | Account Rep | Start Date | End Date | Call Date | Current Date | Progress | Status | Estimated Amount | Actual Amount | Gross Profit
PSG - 6503 Orono Court | 5492 |  | W | 2 | 5 | 7 | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-06-04 | 90% | Invoiced | 2869.03 | 3163.6
PSG 8204 Tory Road | 5496 | 5492 | A | 2 | 5 | 7 | 2024-04-04 | 2024-04-11 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 730 | 730 | 255.75
PSG 8204 Tory Road | 5497 | 5496 | A | 2 | 5 | 7 | 2024-04-04 | 2024-04-11 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 730 | 730 | 255.75
PSG 6927 Mary Caroline Cir | 5505 | 5497 | W | 2 | 5 | 7 | 2024-04-08 | 2024-04-13 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 13646.34 | 14646.85
Georg Schwarz | 5507 | 5505 | O | 9 | 9 | 7 | 2024-04-08 | 2024-04-15 | 2024-06-04 | 2024-06-04 | 85% | Complete
Elizabeth Olson | 5513 | 5508 | PO | 6 | 6 | 7 | 2024-04-10 | 2024-04-17 | 2024-05-12 | 2024-06-04 | 85% | Complete
PSG 5900 Surrey Hill Place | 5489 | 5513 | A | 2 | 6 | 7 | 2024-04-11 | 2024-04-18 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 6149.98 | 6149.98
PSG 6627 Burlington Pl | 5141 | 5589 | R | 3 | 3 | 7 | 2024-04-12 | 2024-04-19 | 2024-06-04 | 2024-06-04 | 0% | Pending |  | 9452.99
BMG 9004 Stratford Lane | 5527 | 5526 | W | 2 | 6 | 7 | 2024-04-17 | 2024-04-24 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 11375.97 | 10237.97
Cory - Miscelaneous Jobs | 5531 | 5528 | RE | 10 | 10 | 7 | 2024-04-18 | 2024-04-25 | 2024-06-04 | 2024-06-04 | 50% | In progress
Cory - Electrical And Generator | 5530 | 5531 | O | 7 | 7 | 7 | 2024-04-19 | 2024-04-26 | 2024-06-04 | 2024-06-04 | 0% | New
PSG 3009 Nicosh Circle | 5533 | 5530 | W | 2 | 6 | 7 | 2024-04-19 | 2024-04-23 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 2473.38 | 2553.84
Dianne Quander | 5534 | 5533 | W | 5 | 5 | 7 | 2024-04-19 | 2024-04-26 | 2024-06-04 | 2024-06-04 | 0% | Pending
Henry Yang & Ping Zhou | 5536 | 5534 | STRR | 2 | 6 | 7 | 2024-04-20 | 2024-04-27 | 2024-06-04 | 2024-06-04 | 90% | Invoiced
PSG 6523 Orono Court | 5540 | 5536 | A | 2 | 5 | 7 | 2024-04-23 | 2024-04-30 | 2024-06-04 | 2024-06-04 | 90% | Invoiced |  | 9838.13 | 6875
Elizabeth Olson - Content Cleaning | 5544 | 5540 | PO | 6 | 6 | 7 | 2024-04-25 | 2024-05-02 | 2024-06-04 | 2024-06-04 | 85% | Complete | 71399.19
Cardinal Forest Party Room | 5546 | 5544 | A | 2 | 6 | 7 | 2024-04-25 | 2024-05-02 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 600 | 600
Sean Van Demark | 5547 | 5546 | W | 2 | 5 | 7 | 2024-04-27 | 2024-05-02 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 5083.17 | 5248.44
Herschel Glenn Gore | 5548 | 5547 | W | 2 | 5 | 7 | 2024-04-27 | 2024-05-01 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 3099.01 | 3012.4
Mary Collier | 5552 | 5447 | W | 5 | 5 | 7 | 2024-05-01 | 2024-05-08 | 2024-06-04 | 2024-06-04 | 0% | Pending
Dave Bell | 5540 | 5552 | R | 3 | 3 | 7 | 2024-05-02 | 2024-05-09 | 2024-06-04 | 2024-06-04 | 5% | Scheduled |  | 14531.28
Anne McGroarty | 5555 | 5540 | W | 2 | 5 | 7 | 2024-05-02 | 2024-05-09 | 2024-06-04 | 2024-06-04 | 90% | Invoiced | 3085.68 | 3755.4
Michael Roschuni | 5556 | 5555 | W | 6 | 6 | 7 | 2024-05-03 | 2024-05-13 | 2024-06-04 | 2024-06-04 | 0% | Pending
Ty Sarvis | 5561 | 5560 | OD | 5 | 5 | 7 | 2024-05-06 | 2024-05-13 | 2024-06-04 | 2024-06-04 | 0% | Pending
John Santoro | 5565 | 5564 | R | 3 | 3 | 7 | 2024-05-07 | 2024-05-14 | 2024-06-04 | 2024-06-04 | 0% | Pending
Anne McGroarty | 5555 | 5567 | R | 3 | 3 | 7 | 2024-05-09 | 2024-05-16 | 2024-05-09 | 2024-06-04 | 0% | Pending |  | 8737.12
Nickolas Bennett | 5572 | 5555 | W | 2 | 6 | 7 | 2024-05-21 | 2024-05-25 | 2024-05-13 | 2024-06-04 | 90% | Invoiced | 1680.46 | 1280.57
Sanar Shamdeen | 5573 | 5572 | M | 4 | 5 | 7 | 2024-05-13 | 2024-05-17 | 2024-05-13 | 2024-06-04 | 0% | Pending
McKenna Walters | 5576 | 5575 | RE | 3 | 3 | 7 | 2024-05-13 | 2024-05-17 | 2024-05-13 | 2024-06-04 | 0% | Pending
The Westchester DeCarlo | 5577 | 5576 | R | 1 | 3 | 7 | 2024-05-13 | 2024-05-17 | 2024-05-13 | 2024-06-04 | 0% | Pending
Babes Wood | 5578 | 5577 | W | 2 | 5 | 7 | 2024-05-14 | 2024-05-17 | 2024-05-14 | 2024-06-04 | 0% | Pending
Scott Reiter | 5580 | 5579 | W | 5 | 5 | 7 | 2024-05-15 | 2024-05-20 | 2024-05-15 | 2024-06-04 | 0% | Pending
BMG 3072 Abingdon St | 5581 | 5580 | M | 2 | 6 | 7 | 2024-05-20 | 2024-05-24 | 2024-05-16 | 2024-06-04 | 90% | Invoiced | 5627.63 | 5627.63
Beverly Cooper | 5583 | 5581 | M | 2 | 6 | 7 | 2024-05-16 | 2024-05-21 | 2024-05-16 | 2024-06-04 | 0% | New
BMG 9004 Stratford Lane | 5584 | 5583 | WF | 2 | 6 | 7 | 2024-05-17 | 2024-05-31 | 2024-05-16 | 2024-06-04 | 90% | Invoiced | 5556.4 | 5556.4
Legacy Community Services | 5585 | 5584 | W | 5 | 5 | 7 | 2024-05-17 | 2024-06-03 | 2024-05-17 | 2024-06-04 | 85% | Complete
Legacy Community Services | 5586 | 5585 | W | 5 | 5 | 7 | 2024-05-17 | 2024-05-21 | 2024-05-17 | 2024-06-04 | 85% | Complete | 2838.05
Legacy Community Services | 5587 | 5586 | W | 5 | 5 | 7 | 2024-05-17 | 2024-05-24 | 2024-05-17 | 2024-06-04 | 85% | Complete
Legacy Community Services | 5588 | 5587 | W | 5 | 5 | 7 | 2024-05-17 | 2024-06-03 | 2024-05-17 | 2024-06-04 | 85% | Complete
PSG 3003 Nicosh Circle | 5590 | 5588 | W | 2 | 6 | 7 | 2024-05-17 | 2024-05-29 | 2024-05-17 | 2024-06-04 | 90% | Invoiced | 1921.04 | 1958.26
PSG 3003 Nicosh Circle | 5591 | 5590 | W | 2 | 6 | 7 | 2024-05-17 | 2024-05-21 | 2024-05-17 | 2024-06-04 | 90% | Invoiced | 3331.41 | 3680.25
PSG 3003 Nicosh Circle | 5592 | 5591 | W | 2 | 6 | 7 | 2024-05-17 | 2024-05-24 | 2024-05-17 | 2024-06-04 | 90% | Invoiced | 4897.17 | 5165.87
BMG 2300 N. Buchanan St | 5593 | 5592 | W | 5 | 5 | 7 | 2024-05-18 | 2024-06-03 | 2024-05-18 | 2024-06-04 | 85% | Complete
PSG 5761 Rexford Ct | 5594 | 5593 | W | 6 | 6 | 7 | 2024-05-18 | 2024-05-23 | 2024-05-18 | 2024-06-04 | 50% | In progress
Sean Van Demark | 5595 | 5594 | R | 3 | 3 | 7 | 2024-05-19 | 2024-05-28 | 2024-05-19 | 2024-06-04 | 50% | In progress |  | 4016.94
Ashraful Alam | 5596 | 5595 | M | 4 | 5 | 7 | 2024-05-19 | 2024-05-22 | 2024-05-19 | 2024-06-04 | 0% | Pending
Allen Tabaka | 5597 | 5596 | M | 2 | 5 | 7 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-06-04 | 0% | New
Legacy Community Services | 5585 | 5597 | R | 3 | 3 | 7 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-06-04 | 0% | Pending
Legacy Community Services | 5586 | 5585 | R | 3 | 3 | 7 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-06-04 | 0% | Pending
Legacy Community Services | 5587 | 5586 | R | 3 | 3 | 7 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-06-04 | 0% | Pending
Legacy Community Services | 5588 | 5587 | R | 3 | 3 | 7 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-06-04 | 0% | Pending
Elizabeth Ray | 5598 | 5588 | M | 4 | 5 | 7 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-06-04 | 0% | Pending
Winifred Williams Paint Interior of House | 5599 | 5598 | RE | 3 | 3 | 7 | 2024-05-21 | 2024-05-28 | 2024-05-21 | 2024-06-04 | 0% | Pending |  | 4709.93
Haymanot Berhe | 5600 | 5599 | W | 6 | 6 | 7 | 2024-05-21 | 2024-05-24 | 2024-05-21 | 2024-06-04 | 15% | Estimating
PSG - 10000 Oakton Terrace Rd | 5601 | 5600 | PO | 6 | 6 | 7 | 2024-05-21 | 2024-05-28 | 2024-05-21 | 2024-06-04 | 15% | Estimating
Tami Jones | 5602 | 5601 | M | 5 | 5 | 7 | 2024-05-21 | 2024-05-24 | 2024-05-21 | 2024-06-04 | 15% | Estimating
Natalie Perilla | 5605 | 5602 | M | 6 | 6 | 7 | 2024-05-22 | 2024-05-25 | 2024-05-22 | 2024-06-04 | 15% | Estimating
Sean Stepp | 5606 | 5605 | W | 5 | 5 | 7 | 2024-05-22 | 2024-05-25 | 2024-05-22 | 2024-06-04 | 50% | In progress |  | 2000
Joanne Flanigan Kitchen & Morning Room | 5611 | 5609 | RE | 3 | 3 | 7 | 2024-05-23 | 2024-05-30 | 2024-05-23 | 2024-06-04 | 15% | Estimating
Jim Hogan | 5612 | 5611 | M | 2 | 6 | 7 | 2024-05-28 | 2024-05-31 | 2024-05-23 | 2024-06-04 | 90% | Invoiced |  | 2094.35
M.E Flow - Aaron Kidwell | 5614 | 5613 | W | 6 | 6 | 7 | 2024-05-23 | 2024-05-28 | 2024-05-23 | 2024-06-04 | 85% | Complete | 2163.78
Judge Glock | 5615 | 5614 | M | 2 | 5 | 7 | 2024-05-23 | 2024-05-28 | 2024-05-23 | 2024-06-04 | 5% | Scheduled
Michael Nelson Jr | 5617 | 5615 | W | 5 | 5 | 7 | 2024-05-26 | 2024-05-30 | 2024-05-26 | 2024-06-04 | 85% | Complete
PSG 5900 UNIT A SURREY | 5618 | 5617 | W | 6 | 6 | 7 | 2024-05-26 | 2024-06-03 | 2024-05-26 | 2024-06-04 | 85% | Complete
PSG 5790 Rexford Unit J | 5619 | 5618 | W | 5 | 5 | 7 | 2024-05-26 | 2024-05-29 | 2024-05-26 | 2024-06-04 | 50% | In progress
Will Berkheiser | 5623 | 5622 | W | 6 | 6 | 7 | 2024-05-28 | 2024-05-31 | 2024-05-28 | 2024-06-04 | 15% | Estimating
Winifred Williams 2nd level wall paint | 5624 | 5623 | RE | 1 | 1 | 7 | 2024-05-29 | 2024-06-07 | 2024-05-29 | 2024-06-04 | 0% | Pending
Joanne Flanigan Powder & Laundry Room | 5625 | 5624 | RE | 3 | 3 | 7 | 2024-05-29 | 2024-06-07 | 2024-05-29 | 2024-06-04 | 15% | Estimating
Natetri Mcclinton | 5628 | 5626 | M | 5 | 5 | 7 | 2024-05-29 | 2024-06-03 | 2024-05-29 | 2024-06-04 | 0% | Pending
Joyce khan | 5630 | 5629 | M | 5 | 5 | 7 | 2024-05-29 | 2024-06-03 | 2024-05-29 | 2024-06-04 | 15% | Estimating
James Dunn | 5631 | 5630 | RE | 3 | 3 | 7 | 2024-05-30 | 2024-06-10 | 2024-05-30 | 2024-06-04 | 15% | Estimating
PSG 8312 Kingsgate Road | 5632 | 5631 | W | 5 | 5 | 7 | 2024-05-30 | 2024-06-03 | 2024-05-30 | 2024-06-04 | 85% | Complete
Sobia Akhtar | 5633 | 5632 | M | 6 | 6 | 7 | 2024-05-30 | 2024-06-05 | 2024-05-30 | 2024-06-04 | 15% | Estimating
Josh Smiroldo | 5634 | 5633 | M | 5 | 5 | 7 | 2024-05-30 | 2024-06-05 | 2024-05-30 | 2024-06-04 | 0% | Pending
Cielo Tembrina | 5636 | 5635 | W | 5 | 5 | 7 | 2024-05-31 | 2024-06-05 | 2024-05-31 | 2024-06-04 | 50% | In progress
Lula Hagos | 5638 | 5636 | M | 2 | 5 | 7 | 2024-05-31 | 2024-06-05 | 2024-05-31 | 2024-06-04 | 5% | Scheduled
Bobby Hosseini | 5641 | 5640 | W | 6 | 6 | 7 | 2024-05-31 | 2024-06-04 | 2024-05-31 | 2024-06-04 | 85% | Complete
Mark Cochran | 5642 | 5641 | M | 4 | 5 | 7 | 2024-06-03 | 2024-06-09 | 2024-06-03 | 2024-06-04 | 0% | Pending
David Creegar | 5643 | 5642 | M | 6 | 6 | 7 | 2024-06-03 | 2024-06-09 | 2024-06-03 | 2024-06-04 | 0% | New
Winifred Williams Bathroom | 5645 | 5644 | W | 6 | 6 | 7 | 2024-06-03 | 2024-06-09 | 2024-06-03 | 2024-06-04 | 50% | In progress
Anita Maginniss | 5646 | 5645 | M | 4 | 6 | 7 | 2024-06-03 | 2024-06-09 | 2024-06-03 | 2024-06-04 | 5% | Scheduled
Kathleen Cote | 5647 | 5646 | O | 9 | 9 | 7 | 2024-06-03 | 2024-06-10 | 2024-06-03 | 2024-06-04 | 50% | In progress
Andrew Engherg | 5648 | 5647 | M | 4 | 5 | 7 | 2024-06-04 | 2024-06-07 | 2024-06-04 | 2024-06-04 | 5% | Scheduled

## Teams
No | Team Leader | Group Head
1 | David Torres | Kimberly Mack
2 | Brenda Matthews | Kimberly Mack
3 | Jennifer Johnson | Kimberly Mack
4 | Kristi Shaw | Kimberly Mack
5 | Sarah Parks | Brian Baldwin
6 | Steven Kerr | Brian Baldwin
7 | Brian Harris | Brian Baldwin
8 | Kenneth Lamb | Brian Baldwin