## Sheet1
Project Name | Task Name | Task | Start Date | End Date | Start to End | Start to today | Progress | Assigned to | Status | Priority
PSG 6503 Orono Court | Monitor drying | 5492 | 2024-04-04 | 2024-04-04 | 0 | 61 | 90% | 15 | Complete | Medium
PSG 6503 Orono Court | Monitor and pick up | 5492 | 2024-04-05 | 2024-04-05 | 0 | 60 | 90% | 16 | Complete | Medium
PSG 6927 Mary Caroline Cir | Water Damage | 5505 | 2024-04-09 | 2024-04-09 | 0 | 56 | 90% | 15 | Complete | Medium
PSG 6927 Mary Caroline Cir | Continue Demo | 5505 | 2024-04-10 | 2024-04-10 | 0 | 55 | 90% | 15 | Complete | Medium
PSG 6927 Mary Caroline Cir | Water Damage | 5505 | 2024-04-11 | 2024-04-11 | 0 | 54 | 90% | 15 | Complete | Medium
PSG 6927 Mary Caroline Cir | Moisture Check | 5505 | 2024-04-12 | 2024-04-13 | 1 | 53 | 100% | 12 | Close | Medium
Elizabeth Olson | Units of Nova to drop one | 5513 | 2024-05-03 | 2024-05-07 | 4 | 32 | 90% | 9 | Complete | High
Elizabeth Olson - Content Cleaning | Continue Content Cleaning | 5544 | 2024-04-27 | 2024-05-02 | 5 | 38 | 90% | 15 | Complete | Medium
Elizabeth Olson - Content Cleaning | Transfer Inventory list | 5544 | 2024-05-09 | 2024-05-09 | 0 | 26 | 90% | 15 | Complete | Medium
Elizabeth Olson - Content Cleaning | Clean clothes at Mount Vernon Laundry | 5544 | 2024-05-03 | 2024-05-03 | 0 | 32 | 100% | 12 | Close | Medium
Henry Yang & Ping Zhou | Trap trap down | 5536 | 2024-04-27 | 2024-04-27 | 0 | 38 | 100% | 12 | Close | Medium
Dave Bell | Meet RE crew on site | 5540 | 2024-06-06 |  |  | -2 | 0% | 1 | Not Stated | Medium
Dave Bell | Dave Bell Rebuild | 5540 | 2024-06-06 | 2024-06-11 |  | -2 | 0% | 10 | Not Stated | Medium
Sean Van Demark | Water Damage | 5547 | 2024-04-28 | 2024-04-28 | 0 | 37 | 90% | 19 | Complete | Medium
Sean Van Demark | Water Damage | 5547 | 2024-04-29 | 2024-04-29 | 0 | 36 | 90% | 20 | Complete | Medium
Sean Van Demark | Moisture Check | 5547 | 2024-05-01 | 2024-05-01 | 0 | 34 | 100% | 11 | Close | Medium
Herschel Glenn Gore | Water Damage | 5548 | 2024-04-28 | 2024-04-28 | 0 | 37 | 90% | 12 | Complete | Medium
Herschel Glenn Gore | Water Damage | 5548 | 2024-04-29 | 2024-04-29 | 0 | 36 | 90% | 20 | Complete | Medium
Daniel Chacon | Estimate Inspection | 5582 | 2024-05-20 | 2024-05-20 | 0 | 15 | 90% | 1 | Complete | Medium
Sean Van Demark | Inspection for Estimate | 5595 | 2024-05-22 | 2024-05-22 | 0 | 13 | 90% | 1 | Complete | Medium
Sean Van Demark | Rising Eagle Rebuild | 5595 | 2024-06-03 | 2024-06-04 | 1 | 1 | 50% | 24 | In Progress | Medium
PSG 5761 Rexford Ct Unit K | Monitor drying | 5594 | 2024-05-22 | 2024-05-22 | 0 | 13 | 90% | 15 | Complete | Medium
BMG 2300 N. Buchanan St | Moisture Check | 5593 | 2024-05-20 | 2024-05-22 | 2 | 15 | 90% | 15 | Complete | Medium
BMG 2300 N. Buchanan St | Moisture Check and Pick UP | 5593 | 2024-05-28 | 2024-05-28 | 0 | 7 | 90% | 15 | Complete | Medium
PSG 3003 Nicosh Circle | Monitor drying | 5592 | 2024-05-22 | 2024-05-23 | 1 | 13 | 100% | 11 | Close | Medium
PSG 3003 Nicosh Circle | Paint affacted Area | 5592 | 2024-05-24 | 2024-05-24 | 0 | 11 | 90% | 22 | Complete | Medium
PSG 3003 Nicosh Circle | Monitor drying | 5591 | 2024-05-20 | 2024-05-20 | 0 | 15 | 100% | 11 | Close | Medium
PSG- 3003 Nicosh Circle | Equipment Pickup | 5590 | 2024-05-22 | 2024-05-22 | 0 | 13 | 100% | 11 | Close | Medium
PSG- 3003 Nicosh Circle | Equipment Pickup | 5590 | 2024-05-28 | 2024-05-28 | 0 | 7 | 100% | 11 | Close | Medium
PSG- 3003 Nicosh Circle | Equipment Pickup | 5590 | 2024-05-29 | 2024-05-29 | 0 | 6 | 100% | 15 | Close | Medium
Legacy Community Services | Sewage Backup | 5588 | 2024-05-17 | 2024-05-18 | 1 | 18 | 100% | 15 | Close | Medium
Legacy Community Services | Moisture Check and Pick UP | 5588 | 2024-05-21 | 2024-05-21 | 0 | 14 | 100% | 11 | Close | Medium
Legacy Community Services | Monitoring | 5588 | 2024-05-20 | 2024-05-20 | 0 | 15 | 90% | 15 | Complete | Medium
Legacy Community Services | Sewage Backup | 5587 | 2024-05-18 | 2024-05-18 | 0 | 17 | 100% | 15 | Close | Medium
Legacy Community Services | Monitor and pick up | 5587 | 2024-05-20 | 2024-05-20 | 0 | 15 | 90% | 15 | Complete | Medium
Legacy Community Services | Moisture Check and Pick UP | 5587 | 2024-05-22 | 2024-05-22 | 0 | 13 | 90% | 15 | Complete | Medium
Legacy Community Services | Monitoring | 5586 | 2024-05-20 | 2024-05-20 | 0 | 15 | 90% | 15 | Complete | Medium
Legacy Community Services | Water Damage | 5585 | 2024-05-24 | 2024-05-24 | 0 | 11 | 90% | 15 | Complete | Medium
Legacy Community Services | Monitoring | 5585 | 2024-05-20 | 2024-05-20 | 0 | 15 | 90% | 15 | Complete | Medium
Legacy Community Services | Moisture Check | 5585 | 2024-05-21 | 2024-05-21 | 0 | 14 | 100% | 11 | Close | Medium
Legacy Community Services | Sewage Backup | 5585 | 2024-05-18 | 2024-05-18 | 0 | 17 | 100% | 15 | Close | Medium
BMG 9004 Stratford Lane | Start Emergency water remediation | 5584 |  |  | 0 | 45447 | 0% | 15 | Not Stated | Medium
BMG 9004 Stratford Lane | Monitor drying | 5584 | 2024-05-22 | 2024-05-22 | 0 | 13 | 90% | 15 | Complete | Medium
BMG 9004 Stratford Lane | Monitor drying | 5584 | 2024-05-28 | 2024-05-28 | 0 | 7 | 90% | 15 | Complete | Medium
BMG 9004 Stratford Lane | Equipment Pickup | 5584 | 2024-05-29 | 2024-05-29 | 0 | 6 | 100% | 15 | Close | Medium
BMG 3072 Abingdon St | Start Remediation | 5581 | 2024-05-20 | 2024-05-20 | 0 | 15 | 100% | 11 | Close | Medium
BMG 3072 Abingdon St | Paint attic board | 5581 | 2024-05-24 | 2024-05-24 | 0 | 11 | 100% | 22 | Close | Medium
BMG 3072 Abingdon St | Monitor drying | 5581 | 2024-05-22 | 2024-05-23 | 1 | 13 | 100% | 11 | Close | Medium
Babes Wood | Water Damage | 5578 | 2024-05-15 | 2024-05-15 | 0 | 20 | 90% | 15 | Complete | Medium
The Westchester DeCarlo | Walk with Aquino Subcontractor | 5577 | 2024-05-17 | 2024-05-17 | 0 | 18 | 90% | 3 | Complete | Medium
McKenna Walters | inspect air return and wall in utility | 5576 | 2024-05-17 | 2024-05-17 | 0 | 18 | 90% | 10 | Complete | Medium
Nickolas Bennett | Start Remediation | 5572 |  |  | 0 | 45447 | 0% | 15 | Not Stated | Medium
John Santoro | Inspection for Rot | 5565 | 2024-05-17 | 2024-05-17 | 0 | 18 | 90% | 10 | Complete | Medium
Anne McGroarty | Water Damage | 5555 | 2024-05-16 | 2024-05-16 | 0 | 19 | 90% | 15 | Complete | Medium
Anne McGroarty | Moisture Check and Pick UP | 5555 | 2024-05-20 | 2024-05-21 | 1 | 15 | 90% | 15 | Complete | Medium
Sean Stepp | Water Damage | 5606 | 2024-06-03 | 2024-06-03 | 0 | 1 | 90% | 22 | Complete | Medium
Sean Stepp | Final clean up | 5606 | 2024-06-04 | 2024-06-04 | 0 | 0 | 90% | 16 | Complete | Medium
Sean Stepp | Water Damage | 5606 | 2024-06-05 | 2024-06-05 | 0 | -1 | 0% | 16 | Not Stated | Medium
Sean Stepp | Moisture Check | 5606 | 2024-05-23 | 2024-05-23 | 0 | 12 | 100% | 11 | Close | Medium
Sean Stepp | Water Damage | 5606 | 2024-05-23 | 2024-05-23 | 0 | 12 | 90% | 10 | Complete | Medium
Sean Stepp | Water Damage | 5606 | 2024-05-28 | 2024-05-28 | 0 | 7 | 100% | 23 | Close | Medium
Sean Stepp | Water Damage | 5606 | 2024-05-29 | 2024-05-29 | 0 | 6 | 100% | 12 | Close | Medium
Sean Stepp | Water Damage | 5606 | 2024-05-30 | 2024-05-30 | 0 | 5 | 90% | 16 | Complete | Medium
Jim Hogan | Start Remediation | 5612 | 2024-05-28 | 2024-05-28 | 0 | 7 | 90% | 15 | Complete | Medium
Jim Hogan | Monitor drying | 5612 | 2024-05-29 | 2024-05-29 | 0 | 6 | 100% | 15 | Close | Medium
Jim Hogan | Monitor drying | 5612 | 2024-05-30 | 2024-05-30 | 0 | 5 | 90% | 15 | Complete | Medium
M.E Flow - Aaron Kidwell | Monitor drying | 5614 | 2024-05-24 | 2024-05-24 | 0 | 11 | 100% | 22 | Close | Medium
Michael Nelson Jr | Moisture Check | 5617 | 2024-05-28 | 2024-05-28 | 0 | 7 | 90% | 22 | Complete | Medium
Michael Nelson Jr | Water Damage | 5617 | 2024-05-29 | 2024-05-29 | 0 | 6 | 100% | 11 | Close | Medium
PSG 5900 UNIT A SURREY | Start Remediation | 5618 | 2024-05-28 | 2024-05-28 | 0 | 7 | 100% | 11 | Close | Medium
PSG 5900 UNIT A SURREY | Monitor drying | 5618 | 2024-05-29 | 2024-05-29 | 0 | 6 | 100% | 15 | Close | Medium
PSG 5900 UNIT A SURREY | Monitor drying | 5618 | 2024-05-31 | 2024-05-31 | 0 | 4 | 100% | 15 | Close | Medium
PSG 5790 Rexford Unit J | Moisture Check and Pick UP | 5619 | 2024-05-30 | 2024-05-30 | 0 | 5 | 90% | 15 | Complete | Medium
Cielo Tembrina | Sewage Backup | 5636 | 2024-06-01 | 2024-06-03 | 2 | 3 | 100% | 15 | Close | Medium
Cielo Tembrina | Moisture Check | 5636 | 2024-06-04 | 2024-06-04 | 0 | 0 | 90% | 11 | Complete | Medium
Bobby Hosseini | Finish remediation | 5641 | 2024-06-03 | 2024-06-03 |  | 1 | 90% | 15 | Complete | Medium
Bobby Hosseini | Equipment Pickup | 5641 | 2024-06-03 | 2024-06-03 |  | 1 | 90% | 15 | Complete | Medium
Bobby Hosseini | Equipment Monitor | 5641 | 2024-06-03 | 2024-06-03 |  | 1 | 100% | 11 | Close | Medium
Winifred Williams | Monitor drying | 5645 |  |  |  |  | 0% | 15 | Not Stated | Medium
Formulas:
Start to today = +TODAY()-[Start Date]